## Slide 1: Creating a Brand New Project using Scrum and Agile Techniques
Matt Turner, Mark Wightman
Red Gate Software

## Slide 2: Overview
Background
Incremental Development + User Feedback
  = Better Product!
If you want to release quicker,
  Automate
  Focus on your backlog
Good estimation means better decisions

## Slide 3: Background

## Slide 4: SQL Source Control
Notes: SQL Source Control is an add-in to SQL Server Management Studio (an environment where most db developers make changes to their dbs)
It’s not a src ctrl system, but the integration provides all the benefits of source control (checking in, updating, history) to db devs in their normal working area
It allows them to put their db schema into a source control system (SVN, TFS).

## Slide 5: Guiding Principles
Ingeniously simple, world class designs
Minimal set of valuable functionality available as soon as possible
Be able to do public releases within one week of sprint end
  Minimise technical debt
  Automate as much as possible
Notes: Regular and converging estimates - encouraging team to spend time estimating and planning & avoid nasty surprises

## Slide 6: Incremental Development + User Feedback = Better Product!
Notes: How focusing on the backlog and building the product incrementally helped us to deliver a higher quality product.
First we’ll talk about the value of feedback, how incremental development helped us to get feedback then we’ll talk about how we achieved this incremental development

## Slide 7: User Feedback is Critical
Previous Red Gate experience
  Don’t trust your assumptions about what customers need and want
  Recreating realistic environments for testing is hard
Intensive Early Access (EA) Program
  Early and regular feedback
  Increased confidence in stability
Notes: PROBLEM
Had learnt from previous Red Gate projects that Early Access releases are a key mechanism for reducing risk of building wrong product, quality not being high enough in the field (real databases hard to replicate in our testing)
SOLUTION
  Early and regular feedback to Reduces risk of building ‘wrong’ product

## Slide 8
Q1 | Q2 | Q3 | Q4 | Q1 | Q2
2009
2010
Prototype
Usability Tests
Dec 2008
Start Prep Mar 2009
Technical Investigations
Initial UI Design
Backlog Preparation
June – August
Sprint 1
21 Aug
v1 Release
30 Jun
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Usability Test
13 Nov
6 EA Releases
2 Beta Releases
1 Release Candidate (average every 3 weeks)
Notes: 2 Developers; 3 Test Engineers; 1 UX; 1 TA
3 months to get to UX sessions
5 months to get 1st EA released; this includes the Christmas holiday

## Slide 9: Mechanisms for User Feedback
Usability Tests
UserVoice
SmartAssembly
Product Support Team/Forum
Notes:   Usability Tests:
  - Usability issues
  UserVoice:
  - Suggest ‘missing’ features
  - Vote on features
SmartAssembly:
- Stability
UserVoice and SmartAssembly – first time we’d used

## Slide 10: Incremental Development
Feedback is most valuable if users have working software they can actually use
Incremental development
  Build product feature by feature
  Vertical slices
  Each feature tested as it is built
Notes: Basic link, commit, and get
Didn’t worry about polish, conflicts, history, etc.
Anything that had a workaround was ignored

## Slide 11: Advantages of Small Stories
  Easy to implement subset of functionality
  Easy to change priorities
  Easier to define and estimate stories
  Focus better during development
  Easier to sync testing with development (in theory)
Notes: Build features incrementally and wait for positive evidence that the ‘gold standard’ solution was necessary
  Change priorities when we had better understanding of what users needed
  Easier to define and estimate stories
  Focus better during development
BUT:
did introduce dependencies between stories, which was difficult
Lots of stories to manage
Started w/ 8 epics (Add/Link/Commit/Get/Notify/Revert/History/Get Previous Version)
130 stories all together just for v1 (> 700 all together)
Average – few team days per story

## Slide 12: “Add database to source control” Story
Notes: Visio mock-up by Dom; Original UI design
End to end workflow: basic link, commit, and get

## Slide 13: ‘Add database…’ stories
Story | Points | Sprint
Add database to Subversion (very basic URL input) | 3 | 2
Automatically include missing trailing / (Added) | 1 | 8
Authenticate Subversion user | 3 | 9
Support https connections to Subversion | 2 | 10
Add database to TFS (very basic URL input) | 8 | 13
Auto-detect TFS/SVN | 3 | 14
Remember Recent Source Control System URLs | 1 | 14
 | 21 | 
Select location by browsing SVN repository | 5 | Not needed
Select location by browsing TFS repository | 5 | Not needed
Add database to local evaluation repository | 5 | Not needed
 | 15 | 
Notes: Dropped 18/39 points that weren’t needed (>25% saving!)
Had functional SVN-only version in sprint 4 with ~20% of total effort
“Install local eval repository” estimate is Mark’s guess

## Slide 14: Sprint 2
>> Add database to Subversion (very basic URL input)
Automatically include missing trailing / (Usability)
Authenticate Subversion user
Support https connections to Subversion
Add database to TFS (very basic URL input)
Auto-detect TFS/SVN
Remember Recent Source Control System URLs
Notes: Hardwired credentials – will only work with our test repository
Only story needed for UX sessions

## Slide 15: Sprint 8
 Add database to Subversion (very basic URL input)
>> Automatically include missing trailing / (Usability)
Authenticate Subversion user
Support https connections to Subversion
Add database to TFS (very basic URL input)
Auto-detect TFS/SVN
Remember Recent Source Control System URLs
Notes: Hardwired credentials – will only work with our test repository
Story we added; more like an annoying bug

## Slide 16: Sprint 10
Add database to Subversion (very basic URL input)
Automatically include missing trailing / (Usability)
>> Authenticate Subversion user
>> Support https connections to Subversion
Add database to TFS (very basic URL input)
Auto-detect TFS/SVN
Remember Recent Source Control System URLs
Notes: Credentials needed for first EA (only supported SVN)

## Slide 17
Sprint 13
Add database to Subversion (very basic URL input)
Automatically include missing trailing / (Usability)
Authenticate Subversion user
Support https connections to Subversion
>> Add database to TFS (very basic URL input)
Auto-detect TFS/SVN
Remember Recent Source Control System URLs
Notes: Finally added TFS support

## Slide 18
Sprint 14
Add database to Subversion (very basic URL input)
Automatically include missing trailing / (Usability)
Authenticate Subversion user
Support https connections to Subversion
Add database to TFS (very basic URL input)
Auto-detect TFS/SVN
Remember Recent Source Control System URLs
Notes: Little extra nice to haves (mostly for our internal team (devs/tests))

## Slide 19: Did we do the right thing?
Only 26 out of >1000 licensed users have requested more
Could have spent x2 effort
  Delayed release (at least 1 more sprint)
It’s all the little things that add-up!
Notes: >20 in uservoice feedback
Only a one-off operation
Not a show-stopper issue (clearly, because 1000 people purchased the product)

## Slide 20: If you want frequent releases: Automate Focus on your Backlog
Notes: Want to talk about two of the techniques that enabled us to do these frequent releases.
Firstly we’ll talk about test automation then I’ll explain how putting the spotlight on our backlog allowed us to address a major timescale challenge to the project

## Slide 21: Our Testing Challenge
175 distinct environments
If we hadn’t automated:
  Several weeks of regression tests per release
  Difficult to justify frequent releases
  High cost for additional environments
Notes:   5 Operating Systems
  7 SQL Server versions
  5 Subversion/Team Foundation Server versions
If we hadn’t automated:
- Lengthy manual testing cycle – probably of the order of several weeks
- Would have made it very difficult to justify frequent releases
Additional Environments:
Both SQL 2008 R2 and TFS 2010 were released during our dev and we wanted to support them.

## Slide 22: Our Solution
Continuous Integration
  Unit tests
  Integration engine tests
Nightly
  Automated GUI acceptance/regression tests in a virtual lab
Manual exploratory testing (per story)
Manual regression testing (per release)
Notes: Unit tests fail the build - ~5 mins
Integration engine tests do not ~1 hr
GUI Tests:
- ~ 6 hrs
- 8 environments
- Important because there is a tight coupling with UI of SSMS, updating the object explorer icons.
2-4 person days of manual regression testing for a release

## Slide 23: Automated GUI Tests
Notes: Run from our continuous integration server, currently nightly
Uses LabManager, our virtualised lab management system
VMAutomation app:
launches a set of VMs, configured with our target environments and installs various supporting apps and assemblies
Installs SQL Source Control using the real installer
Then runs tests built using Ranorex which simulate user actions within SQL Source Control and SSMS. These tests typically set up some sort of state, interact with the product and verify that the user interface state is what we expect.
Results returned to CruiseControl and browsable just like any other automated tests
Have caught many regressions, ranging from simple UI glitches to product crashes.

## Slide 24: Results
Advantages
  Much less manual testing for each release
  More confidence in builds
  Simple to test additional environments
Disadvantages
  A lot of effort to build infrastructure
  Hard to make them reliable
  Can be time-consuming to build new tests
Notes: Advantages
Much less manual testing
1 run of the automated GUI tests is about 4 weeks of a test engineer
Obvious implications for the length of the project and ability to be agile
Also implications for the sanity of our test engineers
More confidence in builds: For the whole team, not just the test engineers
Simple to test additional environments:
Disadvantages
Infrastructure took a lot of effort to get right and took a lot of the team’s focus – test engineers and developers. But we think we can now use that infrastructure cheaply on future projects and are in the process of trying that.
Hard to make them reliable: Don’t always greenlight but the test engineers usually know whether failures are real product failures or not.
TODO: Time-consuming – is this getting quicker as we gain skills?
Conclusion
We feel like the effort we put into automating tests, including GUI automation, was a big success factor for this project. Without it we would have found it difficult to do frequent releases and we wouldn’t have got the level of feedback from customers that we wanted.

## Slide 25: Focus on your Backlog
Notes: Now I’d like to talk about how we put a lot of effort into our product backlog for this project and how that helped us.

## Slide 26: The Product Backlog
Incremental approach needed small, well-written stories
Well-formed backlog early in project
Continuous backlog grooming and reprioritisation
Notes: Stephanie talked about the incremental approach we took and the benefits that gave us. But that was only possible because we split the features into quite small stories and made sure the stories were very well written.
To give you a feel for the size of our stories, we typically completed about 5 stories per 2 week sprint
For this project we made a significant effort in preparing a comprehensive backlog at the start of the project.
Stephanie and David, our product manager, also spent a few hours every week grooming the backlog. By that I mean: reviewing stories, making sure prioritisation was correct, ensuring stories weren’t too big (or small), making sure stories were well-written and clear to the team and looking for opportunities to split out work that wasn’t really needed.
Our perspective is that that effort more than paid for itself in keeping the project focused on the key priorities and providing a clear direction for the team.

## Slide 27: Up Front Preparation
Advantages
  Well-refined product backlog
  Better estimate of overall size of project
Disadvantages
  Lots of meetings
  Team started to get bored
  Not very ‘agile’
Notes: I just want to talk a little more about that upfront effort to create a comprehensive backlog.
It happened that Stephanie did have some time before her project team were available to do more preparation than we have typically done before and one of the things she was able to do was spend time writing the backlog with the product manager’s help.
That gave us some advantages…
Our conclusion is that effort invested in backlog is critical. It doesn’t need to be a huge amount of time – we’ve certainly got quicker at this over time, but it will pay you back. I’d like to give you a practical example of how that effort paid us back…

## Slide 28: Can you release it sooner?
Competitor launch set for June 2010
We had to be in the market!
But we knew this wasn’t likely…
Notes: Important: Why? To offer an alternative solution as customers were evaluating the Visual Studio solution. Had to be something they could try out, not just see information about.

## Slide 29: How we knew we had a problem
January
2011
Notes: If we maintained mean velocity with NO growth in backlog, we’d be 2 months after we wanted to be (end August)
We felt best-case was unrealistic
Worst-case was unacceptable
We knew there were two things we could do: Add people to the team and reduce scope of v1.
We did add a couple of people to the team but we were very cautious about our ability to solve the problem through just this approach. We knew that really the majority of the solution had to be in reducing the size of the backlog.

## Slide 30: Reducing the backlog size
Dropped some features entirely until v1.1
  Limited scope for this
Split stories
  The 80/20 rule
Applied very strict prioritisation
Challenged team to cut stories
  “Is it more important than … ?”
  New team members challenged assumptions
Notes: TFS: We knew we hadto do this because it doubled our market share

## Slide 31: What Happened?
Notes: Trimmed backlog by 20% in November (700-560) then another 15% in Feb (560-480)

## Slide 32: Good Estimation Means Better Decisions
Notes: Finally I’d like to briefly talk about how the estimating techniques that the team used gave us valuable information and enabled us to make better decisions throughout the project.

## Slide 33: What We Did
Before sprint 1:
  Estimated (most of) backlog
  Estimated velocity range
  Derived earliest/latest dates for release
  Backed up by gut feel
After a few sprints:
  Updated predictions using observed velocity data

## Slide 34: Spikes
Used spikes frequently:
  To de-risk
  When we couldn’t estimate
  Team started to insist on this if they couldn't estimate

## Slide 35: It Worked!
Team’s initial velocity estimates:
  Worst case = 19
  Most likely = 23
  Best case = 34
  Derived project lengths backed up by gut feel
Actual mean velocity over project = 22

## Slide 36
Notes: Trimmed backlog by 20% in November (700-560) then another 15% in Feb (560-480)

## Slide 37: Good Estimation Helps
Team tried hard to estimate stories carefully
Stephanie and David used numbers to evaluate options
Felt like we had good understanding of status throughout
  Backed up by gut feel
Better decision making
Notes: Carefully doesn’t mean spending a lot of time on each story, but they did take it seriously and were thoughtful about it

## Slide 38: Conclusions

## Slide 39: Conclusions
Incremental development and Early Access releases helped us to build the right product
  Test automation was critical
Focusing on the backlog helped us to build it quicker
Effective estimation and planning helped us to make good decisions